## Checklist
Checklist
Event: Hypothetical Heatwave
Date:
Time:
Venue:
Task | Target Date | Person Resonsible | Status | Notes
Project Funding
Develop Project Brief
Seek funding from potential partners
Recruit in-kind sponsorship
Heatwave Scenario
Develop heatwave hypothetical scenario
Interview panelists to understand and include their expertise
Review & Feedback of Draft Scenario
Work with Facilitator to further develop scenario
Final check of scenario
Script for news and emergency service announcements
Script for BoM video
Running Sheet / Speaking notes / presentation etc
Running Sheet - provide to facilitator, panellists, stallholders, staff and volunnteers
MC Speaking notes
Powerpoint presentation
Music and sound effects
Lighting
Facilitator
Book Facilitator
Brief Facilitator
Panellists
Book Panel Member 1 - Emergency Services
Book Panel Member 2 - Homeless
Book Panel Member 3 - Housholders
Book Panel Member 4 - Red Cross
Book Panel Member 5 - Council
Book Panel Member 6 - State politician
Book Panel Member 7 - Hospital:
Book Panel Member 9 - Beureu of Meteorology
Book Panel Member 10: Eco Developer
Book Panel Member 11: Police
Book Panel Member 12: School or childcare rep
Book Panel Member 13: Natural Resources
Book Panel Member 14: SA Power Networks
Book Panel Member 15: Transport
Collect head shot photos and bio of each panellists
Brief Panel members
People
Volunteers - for ushering / tickets / set up / pack up /
Staff
Create a list of contact details including names / role / phone / email / secondary person
Venue
Book Venue
Confirm Venue Booking
Logistics & requirements of facility eg, what we need
Develop site plan & map
Background Music during networking & start & end of Hypothetical
Confirm number of stalls, table and chairs
Oranise the screen switching from cartoonist, to homeless pics, to broadcast etc
Smoke Machine
Ticketing & RSVPs
Eventbrite Set up
Eventbrite editing
Ipad or Iphone available with Eventbrite app downloaded for ticket checks
Testing/ teaching door person on use of app
Processing tickets for people who dont have online access
Confirming numbers
Confirm RSVPs
Advertising / Marketing / Media
Marketing and Media Kit (flyer, poster, email invite etc)
Send promo material to partners to distribute through networks
Promote on partner website & socials
Send to facilitator, panel members, stall holders to distribute
Put up posters / flyers at partner buildings
Media Release
Notify Customer Services of all partner organisations
Add to customer 'on hold' messages ?
Request other networks to promote
Talk back radio with pannel members being interviewed
Create a FB event
Stall Holders
Invite stallholders
Layout for stalls
Briefing for stallholders
Parking for stall holders
Staff to help set up
Catering
Select menu & quantities
Obtain quote for catering
Confirm menu
Update catering numbers one week before event
Vox Pop / Video / Photography
Videographer to film event
Photographer: key people, facilitator, panel memebers, stalls, networking, etc
Photos consent forms
On the Day
Acknowlegement to Country
Tickets at the door
Registrations Tables
Print eventbrite registrations
Print event run sheet for facilitator, panel, and more
Volunteers & Staff
Establish a plan for set up and pack up
blu tac / sticky /scissors / pens / pins
Reserved seating for key staff / print
Sheet for people to provide their details so they can recieve the powerpoint presentation and Resilient south updates
Water
iphone / charger
ipads
Running Sheet
Risk Management
Obtain Public Liability of stall holders
Parking
Develop a Risk Management plan
Frist aid officers on site
Access to first aid kits
After Event
Draft report for Councils
Evaluation
Create a thank you's list of people
Thank you emails / letters
Articles for community newsletters & social media
Load videos onto web and promote in socials
Promote success in all media streams used
Debrief meeting

## Budget
Heatwave Hypothetical Budget
OUTGOINGS |  |  |  | INCOMINGS |  |  | Number of people Attending
Item | Projected Cost | Actual Cost (ex GST) | Comments | Organisation | Amount | Comments
Consultants
Facilitatator
Scenario Development
Venue
Theatre Room Hire + Technician
Additional Chairs / Tables
|  |  |  | TOTAL | 0
Advertising
Print advertising
Catering
Cocktail Food / Drinks
Audio / Visual
Filming Hypothetical & technical support
Vox Pops event film
Photographer
Music
Smoke machine
Live Cartooning
Performances / Art
Miscellaneous
Stationary
water bottles
Speaker Gifts
TOTAL | 0 | 0